## Study Plan
Kick-Off Date | 2022-10-24
Initial Black Hole | 2023-01-09
Daily Working Hours | 8
Weekly Working Days | 5
Weekly Working Hours | 40
Error Margin | 30%
[7 empty] | 15 months |  | 42Evaluators
30% over intra expectations
|  | Intra expected time(H) | Personal Expected time | # Working Days | Starting Date | Expected Finish Date | # Months | Real Finish Date | Gained BH Days | Expected BH Date after
Rank 0 | libft | 70 | 91 | 11.375 | 2022-10-24 | 2022-11-08 22:12 | 1 |  |  | FALSE
Rank 1 | ft_printf | 70 | 91 | 11.375 | 2022-11-10 22:12 | 2022-11-26 20:24 | 2 |  |  | TBCalculated
| get_next_line | 70 | 91 | 11.375 | 2022-11-28 20:24 | 2022-12-14 18:36 |  |  |  | TBCalculated
| born2beroot | 40 | 52 | 6.5 | 2022-12-16 18:36 | 2022-12-25 21:00 |  |  |  | TBCalculated
Rank 2 | push_swap | 60 | 78 | 9.75 | 2022-12-27 21:00 | 2023-01-10 12:36 | 2 |  |  | TBCalculated
| minitalk / pipex | 50 | 65 | 8.125 | 2023-01-12 12:36 | 2023-01-23 21:36 |  |  |  | TBCalculated
| so long / FdF / fract-ol | 60 | 78 | 9.75 | 2023-01-25 21:36 | 2023-02-08 13:12 |  |  |  | TBCalculated
Rank 3 | philosophers | 70 | 91 | 11.375 | 2023-02-10 13:12 | 2023-02-26 11:24 | 3 |  |  | TBCalculated
| minishell | 210 | 273 | 34.125 | 2023-02-28 11:24 | 2023-04-17 06:00 |  |  |  | TBCalculated
Rank 4 | NetPractice | 50 | 65 | 8.125 | 2023-04-19 06:00 | 2023-04-30 15:00 | 3 |  |  | TBCalculated
| cub3d / MiniRT | 280 | 364 | 45.5 | 2023-05-02 15:00 | 2023-07-05 07:48 |  |  |  | TBCalculated
| CPP [00--04] | 42 | 54.6 | 6.825 | 2023-07-07 07:48 | 2023-07-16 21:07 |  |  |  | TBCalculated
Rank 5 | CPP [05 - 09] | 140 | 182 | 22.75 | 2023-07-18 21:07 | 2023-08-19 17:31 | 4 |  |  | TBCalculated
| Inception | 140 | 182 | 22.75 | 2023-08-21 17:31 | 2023-09-22 13:55 |  |  |  | TBCalculated
| webserv / ft_irc | 200 | 260 | 32.5 | 2023-09-24 13:55 | 2023-11-09 01:55 |  |  |  | TBCalculated
Rank 6 | ft_transcendence | 245 | 318.5 | 39.8125 | 2023-11-11 01:55 | 2024-01-05 19:37 | 2 |  |  | TBCalculated
Formulas:
Starting Date = if([Real Finish Date, row above]>0,[Real Finish Date, row above],[Expected Finish Date, row above])+2
Expected Finish Date = [Starting Date]+E11*7/B5